## VISION
Implementation Plan
What is the vision?
|  | What are the objectives? | What does success look like
Objective 1
Objective 2
Does it Work
Example 1
Example 2
Is it useful
Example 1
Example 2

## Timeline
RedOptima Private Pilot Programme | Week | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
RTA: | Date | 2022-09-09 | 2022-09-16 | 2022-09-23 | 2022-09-30 | 2022-10-07 | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-25
LEGEND
Ongoing/Scheduled | Original Timeline
Completed |  |  |  | Pilot NDA Signature
Scoping & Legal | NDA
Private Pilot Programme Overview
Vision, Objectives alignment
Scoping the Procurement Path
Inception Meeting
Inception Meeting & Product Creation | RedOptima Portal (Education and Training)
Data Product Order Request
Data Extraction, Algorithm Run, and Report Execution
Data Validation
Export and DQ Checks
Delivery & Business Case | Product Delivery and Operational Tests
Part 1 Analysis: Does it Work?/Areas of Interest.
Part 2 Analysis: Is it useful?/ Points of Interest
Prelim-Exec Presentation
Building the Business Case
Executive Presentation
| Task | Status: |  |  |  |  | Delays: | Blockers:
NDA
Private Pilot Programme Overview
Vision, Objectives alignment
Scoping the Procurement Path
Inception Meeting
RedOptima Portal (Education and Training)
Data Product Order Request
Data Extraction, Algorithm Run, and Report Execution
Data Validation
Export and DQ Checks
Product Delivery and Operational Tests
Part 1 Analysis: Does it Work?/Areas of Interest.
Part 2 Analysis: Is it useful?/ Points of Interest
Prelim-Exec Presentation
Building the Business Case
Executive Presentation

## Mutual Action Plan
|  | RedOptima Account Manager | Kam Hussain | [6 empty] | Yes
|  | RTA Project Owner | [7 empty] | No
RTA Project Manager
Requirements | Q # | Items | RTA Stakeholder | Expected Week of Response from RedOptima | Expected Week of Response From RTA | Action for RedOptima | Response from RTA | Action for RTA
Legal / Vendor Onboaring | 1 | Has RedOptima shared the standard NDA? |  | N/A | N/A | N/A | N/A | N/A | Yes
| 2 | Who is the main point of contact for the legal review? |  | N/A | N/A | N/A | N/A | N/A | Yes
| 3 | First return of NDA with any potential initial redlines | [RTA legal representative] | N/A | N/A | N/A | N/A | N/A | Yes
RedOptima Engagement Scope | 4 | Which entities will be included in the Pilot? a) Your Network + (Neighbour, Police Force, Combined Authority?) b) Projects, departments / division, vendors, locations (you can select multiple entities) - Road Safety Education - Road Safety Engineering - Highways Developemtn Control - Active Travel - Asset Management **Curate an organsiational chart.**
| 5 | Have you briefed relevant internal stakeholders on the engagement with RedOptima? Do you have buy-in from relevant internal stakeholders to involve them later on in the pilot or post Pilot?
| 6 | The budget required for a 1 year subscription is £x (y km) Who are the signatories and/or committee involved to approve this budget upon conclusion of the Pilot?
| 7 | Are you clear internally on the direct award/ procurement process? Have you clearly relayed the direct award/procurement process to RedOptima?
Technical requirements | 8 | What GIS Systems and/or dashboard do you use to view and interpret network risk and highways data? | [RTA member responsible for tech setup]
| 9 | Can you provide a list of Data Sources that you use for a) Road safety remediation b) Highways management | [RTA member responsible for tech setup]
| 10 | How do you currently use your data sources to remediate collision risk?
| 11 | How do you currently map risk on your network (i.e. Link/Node schema)?
| 12 | Who is the main point of contact for technical setup management (I.e Road safety GIS person) ?
| 13 | Have RO requested SCRIM/SCANNER Road Condition Data for data validation?
| 14 | Have RO requested weather dataor data validation? (wind, rain, temperature, etc)
| 15 | Have RO requested non-AADT traffic/speed data for data validation?
Infrastructure Setup | 16 | Has education and training been provided? | [RTA member responsible for tech setup]
| 17 | Has access to the RedOptima Portal been given? Can RTA User login, navigate to Order form, and order successfully? | [RTA member responsible for tech setup]
| 18 | Are you able to successfully download and extract the encrypted data analytics?
0
Value Delivery | 19 | Have you been able to conduct basic analysis functions like thematic mapping, filtering and sorting on the delivered reporting?
| 20 | Are you able to explain RedOptima analytics using the Data Dictionary?
| 21 | DOES IT WORK? Have you asked clear problem questions to be answered by RedOptima using the data or have you given free reign to the RedOptima Account Manager to present proof the product works?
| 22 | IS IT USEFUL? Can you identify relevant use cases to address? Are you able to demonstrate use cases using various GIS analysis methods to begin adding value to road safety challenges you face?
| 23 | Have you independent of your account manager, reviewed the Areas/Points of Interests and agree to the conclusions drawn? Parts of the conclusions from this deck will be used as material for the final executive presentation.
| 24 | Are you able to explain your initial findings internally using all of the tools above?
| 25 | PRELIM EXEC PRESENTATION: Has the RTA been clear as to the success/failure of the pilot so far? If falling short, what can be improved? If succeeding, can the pilot be accelerated by finishing at the prelim exec presentation?
Business Case | 26 | Have you scheduled an executive presentation and briefed the relevant stakeholders?
| 27 | Has the Account Manager drafted the Executive Presentation?
| 28 | Has the first draft been reviewed on a call by both Parties? Have clear next steps been identified?
| 29 | Have you reviewed the material in advance of the meeting with relevant internal stakeholders and sought their input?
| 30 | Has the final executive presentation been reviewed and agreed upon by your RedOptima Account Manager?

## Notes
Meeting | Date | Notes
Inception meeting
Note on A1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Not sure of the point of this tab. Why is it here and unpopulated?